## Functional Release Plan
Task | Use Case | Sprint C | Sprint D | Sprint E | Sprint F | Backlog | Invalid
Novel SSO Integration
Ability to login as instructor or student by authenticating against Novel |  | X
Instructor Class Group Definition
Ability for a student to view their scorecard by clicking on the “My Gradebook & Scorecard” link from the homepage (partly implemented) |  | X
Ability for instructor to view the “Grading Area” when the “My Gradebook & Scorecard” link is clicked from the homepage |  | X
Ability to view the list of students enrolled in the class on the homepage of the “Grading Area” |  | X
Ability to view the list of groups in the course in the left hand panel of the Grading Area |  | X
Ability to create a new group by clicking the “Create Group of Group Set” link |  | X
Ability to display group creation wizard (Agilix component) in F&E when creating groups |  | X
Ability to refresh left hand panel with the newly created groups |  | X
Ability to display the breakdown of users to groups in selected group set |  | X
Ability to display group member last login date as part of PX UI |  | X
Ability to edit existing groups |  | X
Ability to clone existing groups from the left hand sidebar | ? |  |  |  |  | X
Ability to delete existing groups from the left hand sidebar | ? |  |  |  |  | X
Ability to email members in individual group using mailto: |  | X
Ability for instructor to apply settings modifications to individual groups or across all groups | ? |  |  | X
Ability for instructor group student discussion submissions | ? |  |  | X
Ability for instructor to create groups for specific assignment | ? |  |  | X
Ability to email group using PX form | ? |  |  |  |  | X
Writing Assignment Enhancements
Ability for student to create / save multiple documents to a single assignment |  | X
Ability to “Save As” a currently open submission and enter a new title for that submission to save it separately |  | X
Ability to enter the name of a document when you are saving it to an assignment |  | X
Ability to delete document that have been created as part of an assignment |  | X
Ability to confirm the submission to an assignment after the “Submit” button is clicked |  | X
Ability for a student to upload html, doc & docx files to an assignment by entering a title and selecting the file from their computer. File is uploaded, transcoded to HTML, and stored as a submission, editable in the WYSYWIG editor like all other submission files |  | X
Ability to browse the “My Writing” area to add existing documents to the assignment |  | X
Ability for a student to upload pdf, ppt files and have them transcoded correctly to html | ? |  |  |  |  | X
Ability to filter the list of student submissions by the group they are a part of | ? |  |  |  |  | X
Ability for an instructor to “Unsubmit” a student submission |  | X
Ability for an instructor to download student submissions in bulk by selecting each submission that they want, and clicking download |  | X
Ability for a student to download their submissions in bulk by selecting each submission and clicking download |  | X
Writing Assignment Design Changes
Move rubric “category and point entry to the right hand side instead of the left |  | X
Rename links displayed for adding resources |  | X
Add the assignment description to the right hand panel for display while the student is taking the assignment |  | X
Peer Review Assignment
Creating
Ability to drag a “Peer Review” from the “Add panel” to the course TOC |  | X
Ability to title and enter the Peer Review description using a WYSYWIG editor |  | X
Ability to select a writing assignment |  | X
Ability for instructor to view the assignment description and policies on the view tab |  | X
Ability for instructor to view the list of submissions for the selected writing assignment on the view tab |  | X
Taking
Ability for student to view the assignment description and policies on the view tab |  | X
Ability for student to view a list of all writing assignment submissions for all students in the course other than their own |  | X
Ability for student to view peer submission in read only html mode by clicking on its title in the list on the view tab |  | X
Ability for student to switch from one submission to another by changing the submission name in the drop down list |  | X
Ability for student to provide “General Feedback” on the submission by clicking “Add Feedback” |  | X
Ability for the student to highlight the content of the paper by selecting it and entering a comment |  | X
INABILITY for the student to share the comment that they entered on the paper |  | X
Ability to browse through the rubrics linked to the assignment when viewing a student submission |  | X
Inability to enter a rubric score for the assignment |  | X
Ability to Save their review by clicking the “Save” button without the save showing up as a submission to the instructor |  | X
Ability to “Submit” the review for a single submission so that the instructor can view submission |  | X
Ability to auto-submit peer reviews after the submission date passes | ? |  |  |  |  | X
Grading
Ability for instructor to view the list of student peer review submissions (NOT THE SUBMISSIONS ON THE WRITING ASSIGNMENT) AND the total # of reviews that each submission is made up of on the “Results” tab |  | X
Ability for instructor to view each student’s peer review submission by displaying their comments to each paper in F&E mode along with a paging function to move from one submission review to the next |  | X
Ability for an instructor to enter a score for the students peer review submission |  | X
Ability for an instructor to change the submission being reviewed by changing the student name in the drop down |  | X
Ability for an instructor to “Save” a student’s score without submitting by clicking the “Save” button |  | X
Ability for an instructor to “Submit” a student’s score by clicking the “Submit” button |  | X
Grade Viewing
Ability for a student to view their final grade for a peer review submission |  | X
Ability for student to view their peer review submission that they saved in “read-only” mode after submission or grading |  | X
My Writing Desktop
Ability for user to view all documents that they have added to their personal course space |  | X
Ability for user to create new documents directly in their My Writing Desktop |  | X
Ability to upload document directly in their My Writing Desktop |  | X
Ability to rename documents in their My Writing Desktop | [6 empty] | X
Ability to delete documents in their My Writing Desktop |  | X
Ability to submit document to a writing assignment directly from their My Writing Desktop |  | X
Ability to add document to an eportfolio from their My Writing Desktop |  | X
Ability to clone documents in the My Writing Desktop | [6 empty] | X
Ability to view all comments attached to ebook content items (notes) from the My Writing Desktop |  | X
Ability to view all comments attached to peer review assignments from the My Writing Desktop |  | X
Ability to delete comments and notes from the My Writing Desktop |  | X
Ability to view all discussion posts in the My Writing Desktop | ? |  |  |  |  | X
Ability to delete discussion posts from the My Writing Desktop | ? |  |  |  |  | X
ePortfolio
Basic Instructor Functionality
Ability for a instructor to view ePortfolio in the left hand panel before ePortfolio has been activated |  | X
Ability for instructor to activate ePortfolio functionality for their course by creating a base “Eportfolio Folder” |  | X
Ability for instructor to create “EPortfolio Folder” structure under the base folder |  | X
Ability for instructor to drag and drop rearrange “EPortfolio Folders” |  | X
Ability for instructor to delete EPortfolio Folders (after confirmation) |  | X
Ability for instructor to assign EPortfolio folders |  | X
Ability for instructor to create rubrics for eportfolio folders |  | X
Ability to view Eportfolio Folder description and policies on the view page |  | X
Ability for instructor to view their EPortfolio folder structure alone by selecting “EPortfolio Structure” in the drop down |  | X
Ability for instructor to view their student’s eportfolio configuration by selecting the student’s name in the drop down |  | X
Basic Student Functionality
Inability for a student to view ePortfolio in the left hand panel before ePortfolio has been activated |  | X
Ability for student to view instructor created folder structure |  | X
Ability for student to add folders to the instructor created folder structure |  | X
Ability for student to reorder/rearrange folders created by the student in the tree structure |  | X
Inability for the student to reorder/rearrange EPortfolio Folders created by the instructor |  | X
Ability for the student to view EPortfolio Folder description, policies, and the items it contains on the EPortfolio Folder view page |  | X
Ability for the student to view only folder description on the view page for a user created folder |  | X
Ability for student to link to the “My Writing” area from any EPortfolio Folder/Folder |  | X
Ability for student to add new HTML content to a Eportfolio Folder/Folder through WYSYWIG editor displayed in F&E mode (Called Reflection) |  | X
Ability to upload html, docx, doc file to an EPortfolio Folder/Folder using same upload functionality used as part of writing assignment |  | X
EPortfolio Display
Ability to view html document added to EPortfolio folder/folder in the right hand panel when it is selected in the left hand EPortfolio structure |  | X
Ability to view comment attached to a content item in the right hand panel (both comment and document are displayed) when it is selected in the left hand panel |  | X
Ability to view a discussion post in the right hand panel when it is selected in the left hand panel | ? |  |  |  |  | X
ePortfolio Assessment
Submission
Ability for student to submit an assigned ePortfolio folder by clicking the “Submit” button on the View tab |  | X
Grading
Ability for an instructor to view the grading panel for a student’s assigned eportfolio folder while browsing that student’s eportfolio view by clicking on the eportfolio folder itself |  | X
Ability for the instructor to enter a grade for the student’s eportfolio folder and save within the standard eportfolio view |  | X
Ability for instructor to grade student’s submission in F&E mode by clicking on link from the standard grading panel |  | X
Ability for instructor to view rubrics created for the assignment as part of the F&E grading view |  | X
Ability for instructor to enter/save rubric scores for the student’s submission as part of the F&E view |  | X
Ability for instructor to save/submit score for the sudent’s submission as part of the F&E view |  | X
Ability for instructor to switch between student submissions using a drop down of submitted student names as part of the F&E view |  | X
Ability for the instructor to open the F&E mode of the grading screen for a student’s submission from the EPortfolio Folder’s results tab |  | X
Grade Review
Ability for the instructor to view complete list of student submissions/grades on the assigned EPortfolio folder’s results tab |  | X
Ability for student to review their graded eportfolio folder |  | X
Assignment Center Enhancements
Ability to schedule an item using the same calendar functionality currently used for the lesson |  | X
Ability to edit a lesson by clicking on “Edit”, while the lesson is selected, from the gear menu |  | X
Ability to delete lesson by clicking on “Delete”, while the lesson is selected, from the gear menu |  | X
Ability to delete content item from a lesson by clicking on “Delete”, while the item is selected, in the gear menu |  | X
Ability to view all assigned content in the filter breakdown, not just lesson based content |  | X
Ability to “Show Deleted” items | ? |  |  |  |  | X
Assignment Center Design Changes
Update button text |  | X
Use 6 week calendar, with correct overlay display |  | X
Improve display of TOC in add panel |  | X
Commenting 2.0
Ability to add links easily to comments (quicklinks 1.0) |  | X
Implement visibility constraints needed for peer review display |  | X
General UI Modifications |  | X
Comment Library 1.0 |  | X
Browsing Control 3.0
Ability to not select the item when browsing to a folder in the TOC |  | X
Ability to identify assigned items by displayed bullet in TOC |  | X
Ability to click once on new content to create it in the existing folder |  | X
Ability to view configured content filters from the homepage and have clicking on them take you to TOC using them |  | X
Ability to access “View/Edit/Hide Delete” functionality in gear menu instead of in links under each TOC item |  | X
Ability to view tool tip on TOC hover of assigned items |  | X
Ability to view tool tip on TOC hover of hidden items |  | X
Ability to have settings tab display item centric panel, depending on content type | ? |  |  |  |  | X
Ability to click twice of add panel item to load up template view/wizard | ? | [5 empty] | X
Ability to view the # of new comments added to a specific ebook page since the use last visited it | ? |  |  |  |  | X
My Resources | ? |  |  |  | X
F&E Option Configured by Content Type | ? |  |  |  |  | X
Browse Control Design Changes
Ability to browse through filter options in drop down control instead of link list |  | X
Changes to look of tab links at the top of the control |  | X
Update of F&E icon |  | X
Update of Next / Back UI |  | X
Ability to drag the left and right hand panels to different widths |  | X
Hidden content style change |  | X
Bold the selected content item in the TOC |  | X
Quiz Editor 2.0
Ability to page through questions in the quiz when viewing an individual quiz item - include adding new question in F&E mode |  | X
Ability to access the advanced HTS Editor by clicking on the “Advanced Edit” link |  | X
Ability to edit graphical questions | ? |  |  |  |  | X
Ability to preview / take quiz with HTS / Graphical questions |  | X
Display Quiz Summary Above Quiz Taking Component |  | X
Modify Preview Language |  | X
Display Results Tab only after submit | ? |  |  |  |  | X
Ability to update quiz question scores by clicking the question point value from the summary screen |  | X
Ability to “Ask Instructor” from within a quiz/homework assignment | ? |  |  |  |  | X
Ability to resume a partially taken homework question item | ? |  |  |  |  | X
Ability for student to “practice” a quiz | ? |  |  |  |  | X
Ability to filter TOC search by question type | ? |  |  |  | X
Ability to filter item banks by question type/learning object | ? |  |  |  | X
Ability to confirm delete, and "don’t show again" the deletion message | ? |  |  |  |  | X
Ability to view improved quiz policies | ? |  |  |  |  | X
Inability to view arrows in quiz taking component for agilix, only external nagivation | ? |  |  |  |  | X
Ebook 1.5
User can add highlights to the text | EB1 |  | X
Users can delete their highlights. | EB2 |  | X
Inability to delete highlights that have replies from other users | EB3 |  | X
An instructor can delete any highlights + notes, even those that have replies as long as they are public | EB4 |  | X
Users can change the color of their own highlights | EB5 |  | X
Users cannot change the color of others’ highlights | EB6 |  | X
Users can identify notes in the view mode by the red triangle that displays next to them | EB7 |  | X
Users can view notes when hovering over highlights | EB8 |  | X
Ability to view glossed terms and their definitions | EB9 |  |  |  |  | X
Users can print an ebook section, notes, or section plus notes from the view mode | EB10 |  |  |  |  | X
Users can copy text from the eBook | EB11 |  | X
Users can access F&E mode through a variety of ways from the eBook view mode | EB12 |  | X
Users can view notes in F&E mode by selecting View Notes ([# of notes]) | EB13 |  | X
Add top note by selecting Add top note | EB14 |  | X
User can get help adding a note by clicking on “Add Note” in highlighter drop-down menu | EB15 |  | X
A user can clear their highlights from an ebook section. | EB16 |  | X
A user can delete their notes from a section of the ebook. | EB17 |  | X
Users can access the Note Settings screen from link in Highlighter drop-down | EB18 |  | X
A user can print a section of the eBook. | EB19 |  |  |  |  | X
A user can print their notes from a section of the eBook | EB20 |  |  |  |  | X
A user can print an eBook section and its associated notes together. | EB21 |  |  |  |  | X
User can add highlights to the text when they are working in F&E mode | EB22 |  | X
A user can delete highlights | EB23 |  | X
Users can change the color of their own highlights | EB24 |  | X
Users cannot change the color of their others’ highlights | EB25 |  | X
Users can copy text from the eBook while in F&E mode | EB26 |  | X
Users can identify notes in the F&E mode by the red triangle that displays next to them | EB27 |  | X
A user can reply to a note or through F&E mode | EB28 |  | X
A user can add a note in F&E mode | EB29 |  | X
A top note is one that is not attached to a highlight. These are similar to what was called, “Feedback” in Peer review | EB30 |  | X
A user can edit their own note | EB31 |  | X
Users can delete a note using the trash icon | EB32 |  | X
An instructor can delete a specific response to a note | EB33 |  | X
A user can make a private note public | EB34 |  | X
A user can make certain public notes private | EB35 |  | X
Once a reply has been added to a public note, a user cannot make that note private. | EB36 |  | X
Users can add different kinds of links to their notes | EB37 |  |  | X
A user can minimize a single note or top note | EB38 |  | X
A user can minimize all notes, including top notes | EB39 |  | X
A user can maximize a previously collapsed single note or top note | EB40 |  | X
A user can maximize all notes, including top notes that were previously hidden | EB41 |  | X
A user can select to show specific notes/top notes and or highlights using the Show menu in F&E mode | EB42 |  | X
A student can view a locked note. | EB43 |  | X
An instructor can lock a note so that no additional responses can be made to it. | EB44 |  | X
An instructor can unlock note so that replies can be made to it. | EB45 |  | X
A user can clear section highlights while in F&E mode | EB46 |  | X
A user can delete section notes while in F&E mode | EB47 |  | X
A user can access the Note settings panel while in F&E mode | EB48 |  | X
User can use a quick note to add a frequently-used comment to a note. | EB49 |  | X
A user can view their Note Library | EB50 |  | X
A user can add their current note to their Note library | EB51 |  | X
A user can use a note from their Note Library | EB52 |  | X
A user can select a note from their Note Library | EB53 |  | X
A user can drag a note within the Note Library to reorder the list. | EB54 |  | X
From within the Note Library, a user can create a note that will be added to their Note Library list. | EB55 |  | X
From within the Note Library, a user can opt to note create a note, and cancel its creation | EB56 |  | X
A user can enter an equation into a note | EB57 |  |  |  |  | X
The student user can modify their notes settings in order to share private notes with other users | EB58 |  | X
Users can decide to unshare notes with other users with whom they previously shared notes. | EB59 |  | X
When users hover over the breadcrumb, the chapter names display | EB60 |  | X
Instructor Home Page Configuration Wizard
An instructor cannot configure the home page while it is locked | SC1 |  | X
An instructor can configure the home page while it is unlocked | SC2 |  | X
Double clicking on an link while the home page is unlocked moves user off of home page and onto content page. | SC3 |  |  |  |  | X
An instructor can reorder the menu items in the left-hand column | SC4 |  | X
An instructor can hide an element in the left hand column from all the users of the course | SC5 |  | X
An instructor can hide an element in the left hand column from all the students course | SC6 |  | X
An instructor can make a left-hand column item that was invisible to all, or invisible to students visible again | SC7 |  | X
An Instructor can rename an item in the left-hand column | SC8 |  | X
An Instructor can add items to the content under the Home menu in the left-hand column | SC9 |  | X
An Instructor can add links to site content to the Course Links section of the home page | SC10 |  | X
An Instructor can add links to content outside of PX to the list of Course Links | SC11 |  | X
An instructor can remove links from the Course Links | SC12 |  | X
An Instructor can hide links in the Course Links list from Students | SC13 |  | X
An Instructor can edit the name of the links to site content that display in the Course Links | SC14 |  | X
An Instructor can reorder a widget within the column by clicking and dragging the top bar of the widget | SC15 |  | X
An Instructor can remove a widget from the home page | SC16 |  | X
An Instructor can add widgets to the homepage | SC17 |  | X
An Instructor can create their own widgets to be added to the homepage | SC18 |  |  | X
An Instructor can collapse widgets so that only their title bar displays | SC19 |  | X
An Instructor can expand widgets that were previously collapsed so that their display completely. | SC20 |  | X
An Instructor can reorder a widget within the column by clicking and dragging the top bar of the widget | SC21 |  | X
An Instructor can remove a widget from the home page | SC22 |  | X
An Instructor can add widgets to the homepage | SC23 |  | X
An Instructor can create their own widgets to be added to the homepage | SC24 |  |  | X
An Instructor can collapse widgets so that only their title bar displays | SC25 |  | X
An Instructor can expand widgets that were previously collapsed so that their display completely. | SC26 |  | X
Quiz Creation 3.0
Ability for an instructor to create a new quiz in eBook | QZ1 |  | X
Ability for instructor to view the home page of a recently created quiz | QZ2 |  | X
Ability for instructor to update the quiz basic information | QZ3 |  | X
Ability for instructor to search the questions banks by using hierarchical navigation | QZ4 |  | X
Ability to edit a question points value inline on the summary screen | QZ5 |  | X
Ability for instructor to search questions by navigating the hierarchy of question banks through the use of the breadcrumb navigation | QZ6 |  | X
Ability to search question banks using filters | QZ7 |  |  |  | X
Ability to View question “usage in assignment” status | QZ8 |  |  |  |  | X
Ability of the instructor to add questions to a quiz by picking individually each question using checkboxes | QZ9 |  | X
Ability to select quesitons randomly | QZ10 |  |  |  | X
Ability to Select questions by predefined criteria | QZ11 |  |  |  |  | X
Ability for instructor to add questions to a quiz by dragging and dropping questions | QZ12 |  | X
Ability for the instructor to create a new question pool | QZ13 |  | X
Ability for the instructor to add questions to an already existing pool | QZ14 |  | X
Ability for the instructor to add questions to an already existing pool by using drag and drop | QZ15 |  | X
Ability to create new question pools with questions | QZ16 |  | X
Ability for the instructor to view the questions assigned to a particular question pool | QZ17 |  | X
Ability for an instructor to edit the basic data of an existing question pool | QZ18 | X
Ability to edit existing question pool “select by type” setting | QZ19 |  |  |  | X
Ability to edit existing question pool “select by difficulty” setting | QZ20 |  |  |  | X
Ability for an instructor to preview the content of a question | QZ21 |  |  | X
Ability to edit a question from a quiz | QZ22 | X
Ability to edit quiz settings | QZ23 | X
Ability to view selected questions from different elements in the hierarchy in a single panel | QZ24 |  |  |  |  | X
Ability of the instructor to view the quiz main page (basic information page) including questions | QZ25 | X
Ability of the student to view the quiz main page (basic information page) | QZ26 | X
Ability of the student to take a quiz | QZ27 | X
Ability to start a diagnostic quiz | QZ28 |  |  |  | X
Ability to finish a quiz | QZ29 | X
Ability to finish a dignostic quiz | QZ30 |  |  |  | X
Ability to view personalized study plan | QZ31 |  |  |  | X
Ability to expand a topic in the personalized study plan | QZ32 |  |  |  | X
Ability to view diagnostic quiz as a student after taking it | QZ33 |  |  |  | X
Ability to Expand a topic in the PSP section of the quiz view | QZ34 |  |  |  | X
Ability to Retake a diagnostic quiz | QZ35 |  |  |  | X
Ability to View submission of a previously taken diagnostic quiz | QZ36 |  |  |  | X
Ability to View diagnostic quiz | QZ37 |  |  |  | X
Ability to View details of the “topics assessed” report | QZ38 |  |  |  | X
Ability to View quiz results | QZ39 |  |  |  | X
Ability to View details of a PSP topic | QZ40 |  |  |  | X
Ability to View single student quiz results report | QZ41 |  |  |  | X
Ability to View details of a PSP topic for a single student | QZ42 |  |  |  | X
Ability to View item analysis report | QZ43 |  |  |  | X
Ability to Answer a multiple-answer question | QZ44 | X
Ability to Answer a multiple choice question | QZ45 | X
Ability to Answer a matching question | QZ46 | X
Ability for the student to answer a short answer question when in quiz taking mode. | QZ47 | X
Ability for the student to answer an essay question when in quiz taking mode. | QZ48 | X
Ability for the student to interrupt the taking of a homework-mode quiz | QZ49 | X
Ability for the student to interrupt the taking of a homework-mode quiz by navigating elsewhere in the UI | QZ50 | X
Ability for the student to resume a previously saved homework quiz | QZ51 | X
Ability for the student to submit a homework quiz for grading | QZ52 | X
Ability to Submit answers for a test mode quiz | QZ53 | X
The system warns the student not to accidentally or prematurely leave the test quiz | QZ54 |  |  |  |  | X
Ability for the user to see a summary of his/her performance on a submitted quiz | QZ55 |  |  |  | X
Search
A user can launch a basic search by entering term(s) into the search bar | BAS1 |  | X
A user can view basic search results in a menu of results | BAS2 |  | X
A user can scroll down/up the results menu to view more results | BAS3 |  | X
A User can view a specific search result by clicking on it in the results menu. | BAS4 |  | X
A user can collapse a search category within the results menu | BAS5 |  |  |  |  | X
A user can expand a search category within the results menu | BAS6 |  |  |  |  | X
A user can access Advanced Search mode | BAS7 |  | X
A user can launch an advanced search from the home page and specify more search criteria | BAS8 |  |  |  |  | X
A user can view the results of an advanced search on the right-hand side of the advanced search screen | BAS9 |  | X
A user can scroll up/down a list of advanced search results | BAS10 |  | X
A user can preview a specific search result | BAS11 |  |  |  | X
A user can open a search result from the advanced search screen | BAS12 |  | X
A user can reopen an advanced search screen & results from a content page | BAS13 |  |  |  | X
A user can close the advanced search result while navigating a content page that was returned in their search results. | BAS14 |  |  |  | X
A user can save their advanced search terms to create a saved search | BAS15 |  |  |  |  | X
A user can access a saved search from the Advanced Search screen | BAS16 |  |  |  |  | X
A user can edit a saved search to modify the search criteria. | BAS17 |  |  |  |  | X
A user can create a copy of a search by naming it another name. | BAS18 |  |  |  |  | X
A user can delete a saved search | BAS19 |  |  |  |  | X
Content Templating
Ability to click more from the gearbox menu to see the Create New Modal Screen | ? |  |  | X
Ability to view list of product's content templates in the gearbox menu | ? |  |  | X
Ability to create new content using the Create New Modal Screen | ? |  |  | X
Ability to view content type details from the Create New Modal Screen | ? |  |  | X
Ability to adjust content settings for the entire class or by course group | ? |  |  | X
Ability to create new course groups based on individual user search from the settings screen | ? |  |  | X
Ability to select used template for an individual content item | ? |  |  | X
Ability to manage course templates from the Template Management modal | ? |  |  | X
Ability to save current template modifications as a new template | ? |  |  | X
Ability to have current template modifications effect all content created using that template | ? |  |  |  |  | X
Ability to view template description in popup over the template settings | ? |  |  |  |  | X
Xbook
Ability to view "read content" in the "You Have Read" widget | ? |  |  | X
Ability to view chapter folder content from the folder view using infinate-scroll | ? |  |  | X
Ability to view bookmarked content from the Favorites menu | ? |  |  | X
Ability to create detivative courses of the Xbook site type | ? |  |  | X
Ability to drag TOC and Bookmark links into the course links as part of the Add Link functionality | ? |  |  |  |  | X
Inability to create any content type other than HTML content in a Xbook site derivative course | ? |  |  | X
Ability to view More Resources for content in the browsing view | ? |  |  |  | X
Ability to replace existing xbook content with item from the more resources tab |  |  |  |  | X
Ability to navigate to and from the assignment center / content browser / my materials through drop down | ? |  |  | X
Ability to view / interact with content created by you in its own management screen | ? |  |  | X
Assignment Center 2.0
Ability to generate couse syllabus categories using a creation wizard | ? |  |  | X
Ability to view Launchpad / new content creation functionality in new modal view | ? |  |  | X
Ability to preview Launchpad module content | ? |  |  | X
Ability to add module to course assignment list as hidden | ? |  |  | X
Ability to view assignment calendar in standard month calendar view | ? |  |  | X
Ability to assign date range to a course module | ? |  |  | X
Ability for course module date range to adjust to the dates of its contained items | ? |  |  | X
Ability to drag items in and out of categories and modules in the Syllabus view | ? |  |  | X
Ability to mark a module as gradeable and have this mean that the grade is a rollup of contained item grades | ? |  |  | X
Ability to preview TOC content as it is being viewed in the Create New Modular window | ? |  |  | X
Ability to assign a grading category to content from the assign tab | ? |  |  | X
Ability to assign a "syllabus category" to content from the assign tab | ? |  |  | X
Ability to see list of other assignments assigned for the set day from the assign tab | ? |  |  | X
Ability to see content that has been assigned, but not assigned a syllabus category at the top of the category groupings | ? |  |  | X
Ability to switch assignment center from syllabus view to assignment pad (original) view | ? |  |  | X
Ability to mouse over items in the assignment center and see floating tool tip of item details | ? |  |  |  |  | X
Ability to see completed assignment list in the assignment pad view | ? |  |  | X
Ability to see past due assignments in the assignment pad view | ? |  |  | X
Multipart Lesson
Ability to view a multipart lesson made up of content with multiple quizes injected inline with content | ? |  |  | X
Ability to take quizzes in the multipart lesson without clicking the "Start Quiz" button | ? |  |  | X
Ability to view item analysis report for the multipart lesson | ? |  |  |  | X